========================================

PROPILOT PROJECT INTELLIGENCE REPORT

========================================

PROJECT:

E-Commerce Website (PROJ001)

MANAGER:

John

PROJECT STATUS:

At Risk

PROJECT HEALTH:

🔴 RED

PROGRESS:

6 of 15 tasks confirmed completed (T01–T06). 3 tasks are in

progress (T07 Cart API at 50%, T09 Frontend Development at 60%,

T10 Checkout at 40%). 1 task is delayed at 0% (T08 Payment

Integration). 5 tasks have not started (T11–T15). An exact

overall completion percentage cannot be reliably calculated from

the available data.

SCHEDULE:

🔴 DELAYED — The original project deadline of 2026-08-30 has

passed. Five downstream tasks (Integration Testing, Security

Testing, UAT, Deployment, Go-Live) have not started, and the

primary blocker remains unresolved.

========================================

EXECUTIVE SUMMARY

========================================

The E-Commerce Website project is past its original deadline and

classified as At Risk. The primary driver of delay is Payment

Integration (T08), which is stalled at 0% progress because the

vendor has not delivered the required API credentials — a

confirmed, externally caused blocker. T08 is an explicit

dependency for Checkout (T10), Integration Testing (T11),

Security Testing (T12), UAT (T13), Deployment (T14), and Go-Live

(T15), meaning the entire remaining delivery pipeline is

currently blocked. Compounding this, the client has not yet

approved the redesigned checkout screen, adding a parallel

approval dependency on T10, and the QA engineer has been

reported unavailable, creating a resource constraint that will

affect the testing phase once upstream blockers are resolved.

The only documented risk in the risk register remains Open with

no mitigation plan recorded. Immediate escalation of the vendor

dependency and parallel resolution of the client approval issue

are the most critical actions available to the project manager.

========================================

CURRENT STATUS

========================================

✅ COMPLETED:

- T01 — Requirements

- T02 — UI Design

- T03 — Database Design

- T04 — Backend Development (confirmed via UPD001)

- T05 — Authentication (confirmed via UPD006)

- T06 — Product API (confirmed via UPD006)

🔄 IN PROGRESS:

- T07 — Cart API (50%) — progressing independently; no blocker

reported

- T09 — Frontend Development (60%) — progressing independently;

no blocker reported

- T10 — Checkout (40%) — partially blocked; waiting on T08

(delayed) and pending client approval of checkout screen

redesign

🔴 DELAYED:

- T08 — Payment Integration (0%) — externally blocked; vendor

has not provided required API credentials; Project Manager

anticipates an approximate 3-day delay

⛔ BLOCKED / NOT STARTED:

- T11 — Integration Testing — cannot start; explicitly blocked

by T08 and T10; QA engineer also currently unavailable

- T12 — Security Testing — cannot start; depends on T11

- T13 — UAT — cannot start; depends on T11; QA resource

unavailable

- T14 — Deployment — cannot start; depends on T12 and T13

- T15 — Go-Live — cannot start; depends on T14

========================================

TOP RISKS

========================================

1. Vendor Has Not Provided Payment Gateway API Credentials

Category: Vendor

Severity: CRITICAL

Probability: HIGH

Impact: T08 is stalled at 0%, directly blocking T10

(Checkout), T11 (Integration Testing), T12

(Security Testing), T13 (UAT), T14 (Deployment),

and T15 (Go-Live). The entire remaining delivery

pipeline cannot proceed until this is resolved.

The only documented risk record for this issue

is Open with no mitigation plan.

Evidence: UPD002 — "Payment gateway integration is delayed

because the vendor has not provided the required

API credentials."

UPD008 — "The project manager expects payment

integration to be delayed by approximately three

days."

---

2. QA Resource Unavailability Threatens Testing Schedule

Category: Resource

Severity: HIGH

Probability: HIGH

Impact: All three testing tasks (T11, T12, T13) are at

0% and Not Started. When upstream blockers are

resolved, QA capacity must be immediately

available. A resource gap at that moment would

add a further sequential delay to an already

compressed schedule.

Evidence: UPD004 — "QA engineer is unavailable for the

next three days."

UPD007 — "Testing cannot begin until payment

integration and checkout are completed."

---

3. Client Approval Pending on Checkout Screen Redesign

Category: Approval

Severity: MEDIUM

Probability: MEDIUM

Impact: T10 (Checkout) depends on both T08 and client

approval. Even if T08 is unblocked, T10 cannot

be finalized without client sign-off. Any

rework requested post-approval would add further

delay to T11 and all downstream tasks.

Evidence: UPD003 — "Client has not yet approved the

redesigned checkout screen."

========================================

DEPENDENCY & IMPACT

========================================

CRITICAL DEPENDENCY CHAIN:

T08 Payment Integration (DELAYED — Vendor Blocked)

↓ [EXPLICIT]

T10 Checkout (BLOCKED — waiting on T08 + client approval pending)

↓ [EXPLICIT]

T11 Integration Testing (CANNOT START — blocked by T08, T10;

T07 must also complete; QA unavailable)

↓ [EXPLICIT]

T12 Security Testing (CANNOT START)

T13 UAT (CANNOT START — QA resource unavailable)

↓ [EXPLICIT]

T14 Deployment (CANNOT START — requires T12 and T13)

↓ [EXPLICIT]

T15 Go-Live (CANNOT START)

Note: T07 (Cart API, 50%) is also an explicit dependency of T11.

While not the primary blocker, T07 must complete before T11 can

start, representing a secondary gate on the testing phase.

---

IMPORTANT DOWNSTREAM IMPACTS:

- Trigger: T08 delayed (vendor — API credentials not

provided)

Affected: T10 — Checkout

Dependency: EXPLICIT

Impact: T10 cannot be fully completed; stalled at 40%

Confidence: HIGH

- Trigger: T08 delayed + T10 blocked

Affected: T11 — Integration Testing

Dependency: EXPLICIT

Impact: T11 cannot start; confirmed by QA Lead

Confidence: HIGH

- Trigger: T11 cannot start

Affected: T12 — Security Testing, T13 — UAT

Dependency: EXPLICIT

Impact: Both tasks cannot start; QA resource constraint

adds compounding risk to T13

Confidence: HIGH

- Trigger: T12 and T13 blocked

Affected: T14 — Deployment

Dependency: EXPLICIT

Impact: Deployment cannot start until both T12 and T13

complete

Confidence: HIGH

- Trigger: T14 blocked

Affected: T15 — Go-Live

Dependency: EXPLICIT

Impact: Go-Live cannot start

Confidence: HIGH

- Trigger: QA engineer unavailability

Affected: T11, T12, T13

Dependency: INFERRED

Impact: Even after upstream tasks complete, QA capacity

may further delay the testing phase

Confidence: MEDIUM

- Trigger: T07 Cart API at 50%, not yet complete

Affected: T11 — Integration Testing

Dependency: EXPLICIT

Impact: T11 may be affected if T07 is not completed

before T08 and T10 are resolved; currently not

the primary blocker

Confidence: MEDIUM

========================================

RECOMMENDED ACTIONS

========================================

1. Escalate the Vendor Dependency for Payment Gateway API

Credentials

Issue Addressed: T08 (Payment Integration) is stalled at 0%

because the vendor has not delivered API

credentials, blocking 6 downstream tasks.

Urgency: 🔴 IMMEDIATE

Evidence: UPD002 — "Vendor has not provided the

required API credentials."

UPD007 — "Testing cannot begin until payment

integration and checkout are completed."

UPD008 — Project Manager anticipates a delay.

T08 = Delayed, 0%. Risk = Open, no

mitigation documented.

Expected Benefit: Unblocking T08 restores the project's path

through T10 → T11 → T12 → T13 → T14 → T15.

---

2. Document a Mitigation Plan for the Open Vendor Dependency

Risk

Issue Addressed: The only documented risk is Open with an

empty mitigation field, while the risk is

actively materializing.

Urgency: 🔴 IMMEDIATE

Evidence: Risk Register: status = Open, mitigation =

empty. UPD002: Vendor unresponsive. Project

is past its original deadline.

Expected Benefit: Provides a fallback strategy (e.g.,

alternative provider, mock/sandbox API for

parallel development) if vendor escalation

does not resolve the issue promptly.

---

3. Schedule a Client Approval Meeting for the Checkout Screen

Redesign

Issue Addressed: Client approval for the checkout screen

redesign is pending, creating a parallel

blocker on T10 alongside the payment

integration delay.

Urgency: 🟠 HIGH

Evidence: UPD003 — "Client has not yet approved the

redesigned checkout screen."

T10 = In Progress, 40%, depends on both T08

and T09.

Expected Benefit: Removes the approval dependency so T10 can

advance immediately once T08 is unblocked,

avoiding a sequential delay at the checkout

stage.

========================================

UPCOMING ATTENTION ITEMS

========================================

⚠️ IMMEDIATE — Vendor escalation: Obtain a firm commitment

from the payment gateway vendor for API credential delivery.

Establish a clear deadline for vendor response.

⚠️ IMMEDIATE — Risk mitigation: Document a formal mitigation

plan for the open Vendor Dependency risk (Risk ID 1),

including a contingency option if the vendor remains

unresponsive.

🟠 HIGH — Client approval: Schedule and complete client

approval of the redesigned checkout screen to remove the

parallel blocker on T10.

🟠 HIGH — Schedule revision: Review and revise the project

schedule and milestone dates. The original deadline of

2026-08-30 has passed; a revised delivery target is needed

to align stakeholder expectations.

🟡 MEDIUM — QA capacity: Confirm the QA engineer's return

date and assess whether additional QA capacity is needed.

Use the current unavailability window to prepare test plans

and test environments in advance.

🟡 MEDIUM — Parallel progress: Actively monitor and support

T07 (Cart API, 50%) and T09 (Frontend Development, 60%) to

ensure both complete before T08 is unblocked, minimizing

the critical path once the vendor issue is resolved.

🟡 MEDIUM — Task ownership: Assign owners to all unassigned

tasks. No task in the ProPilot Tasks table currently has an

owner recorded, creating an accountability gap across the

project.

🟡 MEDIUM — T10 monitoring: Increase monitoring of Checkout

(T10) as a dependency-critical gateway task. Any additional

slippage in T10 will cascade through all remaining testing

and delivery phases.

========================================

⚠️ DECISION SUPPORT NOTICE

========================================

This report provides decision support based on available project

data. All recommendations are for the project manager's

consideration. Final decisions remain the responsibility of the

project manager.

========================================